## Sheet1
BHHS Class of 1974 Technology Committee Project Schedule
Task Number | Priority | Dependencies | Start Date | End Date | Estimated Effort | Status | Description
1 | High | Randy Sheinbein | 2023-07-11 | 2023-07-12 | 2 Hrs | Complete | Get Website - Purchase Hosting From Provider
2 | High | Task 1 | 2024-07-12 |  | 24 Hrs | In Process | Point Domain Name Server to URL Inform Mark Sheppard of IP address This will take Mark about 5 minutes to configure the DNS record, it may take up to 2 days to reach all domain name servers
3 | High | Tasks 1 & 2 |  |  | 4 Hrs |  | Set up basic theme (black, white orange)
4 | Medium | Task 3 |  |  | 4 Hrs |  | Put holding web page in place Welcome to the BHHS Class of 1974 50th Reunion Website
5 | Medium | Task 4 |  |  | 16 Hrs |  | Set up committee pages
6 | High |  |  |  | 2 Hrs |  | Set up privileged user logins
7 | Medium |  |  |  | 8 Hrs |  | Create forms for committee meeting minutes
8 | High | Task 3 | 2024-01-01 |  | TBD |  | Set up ecommerce portion of website for purchasing tickets
9 | High |  | 2023-07-31 |  | 8 Hrs |  | Create Process for Contact Spreadsheet Update
10 | High |  | 2023-10-31 |  | 2 Hrs |  | Mail blast delivery system