## Sheet1
BHHS Class of 1974 Technology Committee Project Schedule
Task Number | Priority | Dependencies | Start Date | End Date | Estimated Effort | Status | Description
1 | High | Randy Sheinbein |  |  | 2 Hrs | Not Started | Get Website - Purchase Hosting From Provider
2 | High | Task 1 |  |  | 24 Hrs |  | Point Domain Name Server to URL Inform Mark Sheppard of IP address This will take Mark about 5 minutes to configure the DNS record, it may take up to 2 days to reach all domain name servers
3 | High | Tasks 1 & 2 |  |  | 4 Hrs |  | Set up basic theme (black, white orange)
4 | Medium | Task 3 |  |  | 4 Hrs |  | Put holding web page in place Welcome to the BHHS Class of 1974 50th Reunion Website
5 | Medium | Task 4 |  |  | 16 Hrs |  | Set up committee pages
6 | High |  |  |  | 2 Hrs |  | Set up privileged user logins
7 | Medium |  |  |  | 8 Hrs |  | Create forms for committee meeting minutes
8 | High |  | 2023-07-31 |  | 8 Hrs |  | Create Process for Contact Spreadsheet Update
9 | High |  | 2023-10-31 |  | 2 Hrs |  | Mail blast delivery system