## Schedule
BHHS Class of 1974 Technology Committee Project Schedule
Task Number | Priority | Dependencies | Start Date | End Date | Estimated Effort | Status | Description
1 | High | Randy Sheinbein | 2023-07-11 | 2023-07-12 | 2 Hrs | Complete | Get Website - Purchase Hosting From Provider
2 | High | Task 1 | 2024-07-12 | 2023-07-12 | 24 Hrs | Complete | Point Domain Name Server to URL Inform Mark Sheppard of IP address This will take Mark about 5 minutes to configure the DNS record, it may take up to 2 days to reach all domain name servers
3 | Medium |  | 2023-07-12 | 2023-07-13 | 4 Hrs | Complete | Put holding web page in place Welcome to the BHHS Class of 1974 50th Reunion Website
4 | High |  | 2023-07-12 |  | 2 Hrs | In Progress | Set up privileged user logins
5 | High |  |  |  | 2 Hrs |  | Buy Divi Theme from Elegant Themes
6 | High | Task 5 |  |  | 6 Hrs |  | Set up basic theme (black, white orange)
7 | High | Ruth Amir |  |  | 1 Week |  | Graphic Design for website
8 | High | Task 7 |  |  | 8 Hrs |  | Apply Graphic Design to website
9 | Medium | Task 8 |  |  | 16 Hrs |  | Set up committee pages
10 | Medium | Task 9 |  |  | 8 Hrs |  | Create forms for committee meeting minutes
11 | High | Events Committee | 2023-07-17 | 2023-09-01 | 8 weeks |  | Select Venue Select Date
12 | High | Task 11 |  |  |  |  | Final Graphic Design with Ad Copy
13 | High | Task 11 |  |  |  |  | Elementary School Reunion web pages
14 | High | Task 12 | 2024-01-01 | 2023-02-28 | TBD |  | Set up ecommerce portion of website for purchasing tickets
15 | High |  | 2023-07-31 |  | 8 Hrs |  | Create Process for Contact Spreadsheet Update
16 | High |  | 2023-10-31 |  | 2 Hrs |  | Mail blast delivery system